## Summary
CROSSMARKET PRICE ANALYZER — PROJECT TRACKER
Q2-Q4 2026 ¦ MVP to v1.5 to v2.0 ¦ Last Updated: 2026-04-10
Phase | Weeks | Milestone | Total | Done | In Progress | Pending | Blocked | % Complete
Phase 0 — Foundation | 1–3 | M1: Foundation | 12 | 11 | 0 | 1 | 0 | 9200%
Phase 1 — MVP Core | 4–10 | M2: Alpha | 37 | 37 | 0 | 0 | 0 | 10000%
Phase 2 — MVP Completion & Polish | 11–14 | M3: MVP v1.0 | 21 | 0 | 0 | 21 | 0 | 0%
Phase 3 — v1.5 Feature Expansion | 15–22 | M4: v1.5 | 19 | 0 | 0 | 19 | 0 | 0%
Phase 4 — v2.0 Full Platform | 23–30 | M5: v2.0 | 25 | 0 | 0 | 25 | 0 | 0%
OVERALL — 114 Total Tasks
PROJECT STATISTICS
Metric | Value | Category | Count
Total Tasks | 114 | Backend | 23
Critical Tasks | 13 | Frontend | 19
Phases | 4 | DevOps/Infra | 11
Duration | ~30 weeks | Testing/QA | 8
LEGEND — HOW TO USE THIS TRACKER
✅ Done | Task completed
🔄 In Progress | Work underway
⏳ Pending | Not started
⏸️ Waiting | Dependency/external
🚫 Blocked | Blocked issue
🔴 Critical | Must for milestone
🟠 High | Important
🔵 Medium | Nice-to-have

## All Tasks
CROSSMARKET PRICE ANALYZER — COMPLETE TASK TRACKER
Update Status column each week. Filter by Phase/Owner/Priority/Status.
# | Phase | Task ID | Task Description | Owner | Type | Priority | Status | Wk Start | Wk Done | Effort (d) | Milestone | Blockers | Notes | Updated
1 | Phase 0 — Foundation | P0-F01 | Provision Docker Compose (MySQL, Redis, RabbitMQ) | DevOps | Infra | Critical | Done |  |  |  |  | M1: Foundation
2 | Phase 0 — Foundation | P0-F02 | Create .NET 9 solution structure (Common + 5 services) | Backend | Dev | Critical | Done |  |  |  |  | M1: Foundation
3 | Phase 0 — Foundation | P0-F03 | Implement Common.Domain (BaseEntity, ValueObjects, Enums) | Backend | Dev | Critical | Done |  |  |  |  | M1: Foundation
4 | Phase 0 — Foundation | P0-F04 | Implement Common.Application pipeline behaviors | Backend | Dev | Critical | Done |  |  |  |  | M1: Foundation
5 | Phase 0 — Foundation | P0-F05 | Configure EF Core MySQL + write all migrations | Backend | Dev | Critical | Done |  |  |  |  | M1: Foundation
6 | Phase 0 — Foundation | P0-F06 | Scaffold React 18 + Vite + Tailwind + shadcn/ui | Frontend | Dev | Critical | Done |  |  |  |  | M1: Foundation
7 | Phase 0 — Foundation | P0-F07 | Configure GitHub Actions CI pipeline | DevOps | Infra | Critical | Done |  |  |  |  | M1: Foundation
8 | Phase 0 — Foundation | P0-F08 | Set up YARP API Gateway with routing rules | Backend | Dev | Critical | Done |  |  |  |  | M1: Foundation
9 | Phase 0 — Foundation | P0-F09 | Implement base UI components (Button, Card, Input...) | Frontend | Dev | High | Done |  |  |  |  | M1: Foundation
10 | Phase 0 — Foundation | P0-F10 | Configure Serilog + OpenTelemetry | DevOps | Infra | Medium | Done |  |  |  |  | M1: Foundation
11 | Phase 0 — Foundation | P0-F11 | Create system architecture diagram | Architect | Docs | Medium | Done |  |  |  |  | M1: Foundation
12 | Phase 0 — Foundation | P0-F12 | Legal review of scraping compliance | External | Legal | Medium | Pending |  |  |  |  | M1: Foundation
12 tasks → Phase 0 — Foundation | 1–3 |  | M1: Foundation
15 | Phase 1 — MVP Core | P1-B01 | Implement Product/Brand/Category domain entities | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
16 | Phase 1 — MVP Core | P1-B02 | Implement PriceSnapshot entity + repository | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
17 | Phase 1 — MVP Core | P1-B03 | Implement ProductService REST API | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
18 | Phase 1 — MVP Core | P1-B04 | Implement QuickLookupCommand (URL→scrape→analyze) | Backend | Dev | High | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
19 | Phase 1 — MVP Core | P1-B05 | Implement ExchangeRateService + Redis cache | Backend | Dev | High | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
20 | Phase 1 — MVP Core | P1-B06 | Implement GetOpportunitiesQuery | Backend | Dev | High | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
21 | Phase 1 — MVP Core | P1-B07 | Unit tests: ProductService domain logic | Backend | Test | Medium | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
22 | Phase 1 — MVP Core | P1-B08 | Unit tests: ProductService handlers | Backend | Test | Medium | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
23 | Phase 1 — MVP Core | P1-B09 | Implement ProductMatch aggregate + repository | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
24 | Phase 1 — MVP Core | P1-B10 | Implement FuzzyMatchingService (Levenshtein+TF-IDF) | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
25 | Phase 1 — MVP Core | P1-B11 | Implement MatchingService REST API | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
26 | Phase 1 — MVP Core | P1-B12 | Implement batch confirm/reject endpoint | Backend | Dev | Medium | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
27 | Phase 1 — MVP Core | P1-B13 | Unit tests: FuzzyMatchingService | Backend | Test | Medium | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
28 | Phase 1 — MVP Core | P1-B14 | Implement OpportunityScore aggregate + repository | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
29 | Phase 1 — MVP Core | P1-B15 | Implement ScoringEngine (weighted multi-factor) | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
30 | Phase 1 — MVP Core | P1-B16 | Implement LandedCostCalculator | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
31 | Phase 1 — MVP Core | P1-B17 | Implement ScoringService REST API | Backend | Dev | Medium | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
32 | Phase 1 — MVP Core | P1-B18 | Unit tests: ScoringEngine + LandedCostCalculator | Backend | Test | Medium | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
33 | Phase 1 — MVP Core | P1-B19 | Set up Quartz.NET job scheduler | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha |  | 2026-04-10
34 | Phase 1 — MVP Core | P1-B20 | Implement Amazon scraper (Playwright) | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
35 | Phase 1 — MVP Core | P1-B21 | Implement Walmart scraper (Playwright) | Backend | Dev | High | Done |  |  | 2026-04-09 |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
36 | Phase 1 — MVP Core | P1-B22 | Implement cigarpage.com scraper (Playwright) | Backend | Dev | Medium | Done |  |  | 2026-04-09 |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
37 | Phase 1 — MVP Core | P1-B23 | Implement Shopee API client (or mock) | Backend | Dev | Medium | Done |  |  | 2026-04-09 |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
38 | Phase 1 — MVP Core | P1-B24 | Implement ExchangeRateUpdateJob (hourly) | Backend | Dev | Critical | Done |  |  | 2026-04-09 |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
39 | Phase 1 — MVP Core | P1-B25 | Implement CostRecalcJob + ScoringJob (6-hourly) | Backend | Dev | Medium | Done |  |  | 2026-04-09 |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
40 | Phase 1 — MVP Core | P1-F01 | Build DashboardPage with OpportunityCard feed | Frontend | Dev | Critical | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
41 | Phase 1 — MVP Core | P1-F02 | Build ComparisonPage (US vs VN, cost breakdown) | Frontend | Dev | Critical | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
42 | Phase 1 — MVP Core | P1-F03 | Build FilterBar with all dashboard filters | Frontend | Dev | High | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
43 | Phase 1 — MVP Core | P1-F04 | Build CategoryPage with category grid | Frontend | Dev | Medium | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
44 | Phase 1 — MVP Core | P1-F05 | Build QuickLookupPage with URL form + results | Frontend | Dev | High | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
45 | Phase 1 — MVP Core | P1-F06 | Build PriceDisplay, ScoreGauge, ConfidenceBadge | Frontend | Dev | High | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
46 | Phase 1 — MVP Core | P1-F07 | Implement React Query hooks for all API calls | Frontend | Dev | Critical | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
47 | Phase 1 — MVP Core | P1-F08 | Build Header + Sidebar layout | Frontend | Dev | Critical | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
48 | Phase 1 — MVP Core | P1-F09 | Add Zustand stores (scoringStore, filterStore) | Frontend | Dev | High | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
49 | Phase 1 — MVP Core | P1-F10 | Build ExportButton (CSV export) | Frontend | Dev | Medium | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
50 | Phase 1 — MVP Core | P1-F11 | Skeleton loading states + ErrorBoundary | Frontend | Dev | Medium | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
51 | Phase 1 — MVP Core | P1-F12 | Responsive layout testing | Frontend | Test | Medium | Done |  |  |  |  | M2: Alpha | Frontend wiring complete — 0 build errors, 2026-04-10 | 2026-04-10
37 tasks → Phase 1 — MVP Core | 4–10 |  | M2: Alpha
54 | Phase 2 — MVP Completion & Polish | P2-B01 | Add Polly resilience (retry + circuit breaker) | Backend | Dev | Critical | Pending |  |  |  |  | M3: MVP v1.0
55 | Phase 2 — MVP Completion & Polish | P2-B02 | Implement outbox pattern for reliable events | Backend | Dev | Medium | Pending |  |  |  |  | M3: MVP v1.0
56 | Phase 2 — MVP Completion & Polish | P2-B03 | Integration tests (Testcontainers) | Backend | Test | Medium | Pending |  |  |  |  | M3: MVP v1.0
57 | Phase 2 — MVP Completion & Polish | P2-B04 | Optimize DB queries (indexes, N+1 fixes) | Backend | Dev | Medium | Pending |  |  |  |  | M3: MVP v1.0
58 | Phase 2 — MVP Completion & Polish | P2-B05 | Add RotatingProxyService for scrapers | Backend | Dev | Medium | Pending |  |  |  |  | M3: MVP v1.0
59 | Phase 2 — MVP Completion & Polish | P2-B06 | Manual shipping/duty cost override | Backend | Dev | Medium | Pending |  |  |  |  | M3: MVP v1.0
60 | Phase 2 — MVP Completion & Polish | P2-B07 | Legal compliance sign-off | External | Legal | Medium | Pending |  |  |  |  | M3: MVP v1.0
61 | Phase 2 — MVP Completion & Polish | P2-F01 | Build PriceHistoryPage with Recharts line chart | Frontend | Dev | High | Pending |  |  |  |  | M3: MVP v1.0
62 | Phase 2 — MVP Completion & Polish | P2-F02 | Build AlertsPage with notification list | Frontend | Dev | Medium | Pending |  |  |  |  | M3: MVP v1.0
63 | Phase 2 — MVP Completion & Polish | P2-F03 | Build SettingsPage with scoring weight sliders | Frontend | Dev | High | Pending |  |  |  |  | M3: MVP v1.0
64 | Phase 2 — MVP Completion & Polish | P2-F04 | Internationalization EN + VI | Frontend | Dev | Medium | Pending |  |  |  |  | M3: MVP v1.0
65 | Phase 2 — MVP Completion & Polish | P2-F05 | Accessibility audit (axe-core) + fixes | Frontend | QA | Medium | Pending |  |  |  |  | M3: MVP v1.0
66 | Phase 2 — MVP Completion & Polish | P2-F06 | E2E tests: Dashboard, QuickLookup, Comparison | QA | Test | Medium | Pending |  |  |  |  | M3: MVP v1.0
67 | Phase 2 — MVP Completion & Polish | P2-F07 | Performance optimization (lazy load, memo) | Frontend | Dev | Medium | Pending |  |  |  |  | M3: MVP v1.0
68 | Phase 2 — MVP Completion & Polish | P2-F08 | Empty states + error states | Frontend | Dev | Medium | Pending |  |  |  |  | M3: MVP v1.0
69 | Phase 2 — MVP Completion & Polish | P2-D01 | Production Docker Compose + health checks | DevOps | Infra | Critical | Pending |  |  |  |  | M3: MVP v1.0
70 | Phase 2 — MVP Completion & Polish | P2-D02 | GitHub Actions CD (auto-deploy staging) | DevOps | Infra | Critical | Pending |  |  |  |  | M3: MVP v1.0
71 | Phase 2 — MVP Completion & Polish | P2-D03 | Prometheus + Grafana monitoring dashboards | DevOps | Infra | Medium | Pending |  |  |  |  | M3: MVP v1.0
72 | Phase 2 — MVP Completion & Polish | P2-D04 | API documentation (Swagger/OpenAPI) | Backend | Docs | Medium | Pending |  |  |  |  | M3: MVP v1.0
73 | Phase 2 — MVP Completion & Polish | P2-D05 | User guide (markdown) for MVP | Scribe | Docs | Medium | Pending |  |  |  |  | M3: MVP v1.0
74 | Phase 2 — MVP Completion & Polish | P2-D06 | Internal UAT | Team | QA | Critical | Pending |  |  |  |  | M3: MVP v1.0
21 tasks → Phase 2 — MVP Completion & Polish | 11–14 |  | M3: MVP v1.0
77 | Phase 3 — v1.5 Feature Expansion | P3-B01 | Implement Lazada Open Platform API client | Backend | Dev | High | Pending |  |  |  |  | M4: v1.5
78 | Phase 3 — v1.5 Feature Expansion | P3-B02 | Implement Tiki scraping | Backend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
79 | Phase 3 — v1.5 Feature Expansion | P3-B03 | Integrate FedEx shipping API | Backend | Dev | High | Pending |  |  |  |  | M4: v1.5
80 | Phase 3 — v1.5 Feature Expansion | P3-B04 | Integrate DHL shipping API (fallback) | Backend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
81 | Phase 3 — v1.5 Feature Expansion | P3-B05 | HS code auto-detection from product name | Backend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
82 | Phase 3 — v1.5 Feature Expansion | P3-B06 | Update tariff tables (monthly refresh) | Backend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
83 | Phase 3 — v1.5 Feature Expansion | P3-B07 | Excel export with formatted sheets (EPPlus) | Backend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
84 | Phase 3 — v1.5 Feature Expansion | P3-B08 | Price stability (rolling 30-day variance) | Backend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
85 | Phase 3 — v1.5 Feature Expansion | P3-B09 | WebSocket server for real-time push | Backend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
86 | Phase 3 — v1.5 Feature Expansion | P3-F01 | WebSocket frontend integration | Frontend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
87 | Phase 3 — v1.5 Feature Expansion | P3-F02 | MarginBarChart component | Frontend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
88 | Phase 3 — v1.5 Feature Expansion | P3-F03 | ScoreRadarChart component | Frontend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
89 | Phase 3 — v1.5 Feature Expansion | P3-F04 | Export: Excel format (SheetJS) | Frontend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
90 | Phase 3 — v1.5 Feature Expansion | P3-F05 | Filter: Source marketplace multi-select | Frontend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
91 | Phase 3 — v1.5 Feature Expansion | P3-F06 | Dashboard: Top movers / biggest changes | Frontend | Dev | Medium | Pending |  |  |  |  | M4: v1.5
92 | Phase 3 — v1.5 Feature Expansion | P3-T01 | Integration tests: all API endpoints | Backend | Test | Medium | Pending |  |  |  |  | M4: v1.5
93 | Phase 3 — v1.5 Feature Expansion | P3-T02 | Load testing (k6) — 50k products | DevOps | Test | Medium | Pending |  |  |  |  | M4: v1.5
94 | Phase 3 — v1.5 Feature Expansion | P3-T03 | Re-generate Swagger API docs | Backend | Docs | Medium | Pending |  |  |  |  | M4: v1.5
95 | Phase 3 — v1.5 Feature Expansion | P3-T04 | Deploy to production | DevOps | Infra | Critical | Pending |  |  |  |  | M4: v1.5
19 tasks → Phase 3 — v1.5 Feature Expansion | 15–22 |  | M4: v1.5
98 | Phase 4 — v2.0 Full Platform | P4-B01 | User auth: JWT + Identity | Backend | Dev | Critical | Pending |  |  |  |  | M5: v2.0
99 | Phase 4 — v2.0 Full Platform | P4-B02 | User registration + login APIs | Backend | Dev | Critical | Pending |  |  |  |  | M5: v2.0
100 | Phase 4 — v2.0 Full Platform | P4-B03 | Saved product watchlist | Backend | Dev | High | Pending |  |  |  |  | M5: v2.0
101 | Phase 4 — v2.0 Full Platform | P4-B04 | NotificationService REST API | Backend | Dev | High | Pending |  |  |  |  | M5: v2.0
102 | Phase 4 — v2.0 Full Platform | P4-B05 | Email notifications (SendGrid) | Backend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
103 | Phase 4 — v2.0 Full Platform | P4-B06 | Telegram bot notifications | Backend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
104 | Phase 4 — v2.0 Full Platform | P4-B07 | Alert threshold engine | Backend | Dev | High | Pending |  |  |  |  | M5: v2.0
105 | Phase 4 — v2.0 Full Platform | P4-B08 | Scheduled report generation | Backend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
106 | Phase 4 — v2.0 Full Platform | P4-B09 | PDF report generation (QuestPDF) | Backend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
107 | Phase 4 — v2.0 Full Platform | P4-B10 | Multi-tenancy (per-user alerts + watchlists) | Backend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
108 | Phase 4 — v2.0 Full Platform | P4-F01 | Login/Register page + JWT auth flow | Frontend | Dev | Critical | Pending |  |  |  |  | M5: v2.0
109 | Phase 4 — v2.0 Full Platform | P4-F02 | Protect routes (redirect unauthenticated) | Frontend | Dev | Critical | Pending |  |  |  |  | M5: v2.0
110 | Phase 4 — v2.0 Full Platform | P4-F03 | User profile page | Frontend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
111 | Phase 4 — v2.0 Full Platform | P4-F04 | Add to Watchlist button | Frontend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
112 | Phase 4 — v2.0 Full Platform | P4-F05 | My Watchlist page | Frontend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
113 | Phase 4 — v2.0 Full Platform | P4-F06 | Alert preferences UI | Frontend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
114 | Phase 4 — v2.0 Full Platform | P4-F07 | PDF export from frontend | Frontend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
115 | Phase 4 — v2.0 Full Platform | P4-F08 | Scheduled reports UI | Frontend | Dev | Medium | Pending |  |  |  |  | M5: v2.0
116 | Phase 4 — v2.0 Full Platform | P4-T01 | Security audit (OWASP Top 10) | Security | Audit | Critical | Pending |  |  |  |  | M5: v2.0
117 | Phase 4 — v2.0 Full Platform | P4-T02 | Full regression test suite (Playwright) | QA | Test | Medium | Pending |  |  |  |  | M5: v2.0
118 | Phase 4 — v2.0 Full Platform | P4-T03 | Penetration testing | External | Security | Medium | Pending |  |  |  |  | M5: v2.0
119 | Phase 4 — v2.0 Full Platform | P4-T04 | Performance benchmark at 50k products | DevOps | Test | Medium | Pending |  |  |  |  | M5: v2.0
120 | Phase 4 — v2.0 Full Platform | P4-T05 | Write v2.0 user documentation | Scribe | Docs | Medium | Pending |  |  |  |  | M5: v2.0
121 | Phase 4 — v2.0 Full Platform | P4-T06 | Production deployment + DNS + SSL | DevOps | Infra | Critical | Pending |  |  |  |  | M5: v2.0
122 | Phase 4 — v2.0 Full Platform | P4-T07 | Soft launch to first external users | Team | Launch | Critical | Pending |  |  |  |  | M5: v2.0
25 tasks → Phase 4 — v2.0 Full Platform | 23–30 |  | M5: v2.0

## Roadmap Timeline
CROSSMARKET PRICE ANALYZER — RELEASE ROADMAP TIMELINE
Weeks 1–30 ¦ MVP Week 14 · v1.5 Week 22 · v2.0 Week 30
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Phase 0 — Foundation | W1–3
Phase 1 — MVP Core | W4–10
Phase 2 — MVP Completion | W11–14
Phase 3 — v1.5 Expansion | W15–22
Phase 4 — v2.0 Full Platform | W23–30
📌 Milestones |  | 3: M1: Foundation; 10: M2: Alpha; 14: M3: MVP v1.0; 22: M4: v1.5; 30: M5: v2.0
👥 Team
Backend | Infra + 5 microservices + workers
Frontend | React SPA + all pages
DevOps | CI/CD + Docker + Monitoring
QA/Testing | Unit + Integration + E2E
Docs/Legal | Documentation + Compliance